## Task Log
Client | PROJECT NAME | Date | Username | Start | Stop | Duration | JOB DESCRIPTION
Henry | PaiSmart Development | 10/04/2026 | Henry | 9:30 AM | 1:00 PM | 3:30 | Phase 1 kickoff: reviewed the RAG knowledge-base scope, identified core modules, and defined the first delivery target around authentication, upload, retrieval, and chat.
Henry | PaiSmart Development | 10/04/2026 | Henry | 2:00 PM | 6:30 PM | 4:30 | Selected the backend and frontend stack: Spring Boot, Java 17, MySQL, Redis, MinIO, Kafka, Elasticsearch, Vue 3, TypeScript, Pinia, Vite, and Naive UI.
Henry | PaiSmart Development | 13/04/2026 | Henry | 9:30 AM | 1:00 PM | 3:30 | Created the backend project structure with controller, service, repository, model, config, client, consumer, exception, handler, and utility packages.
Henry | PaiSmart Development | 13/04/2026 | Henry | 2:00 PM | 6:30 PM | 4:30 | Configured Maven dependencies for web APIs, security, JPA, Redis, WebSocket, WebFlux, MinIO, Apache Tika, Kafka, Elasticsearch, JWT, validation, and testing.
Henry | PaiSmart Development | 14/04/2026 | Henry | 9:30 AM | 1:00 PM | 3:30 | Designed the MySQL schema for users, uploaded files, chunk records, document vectors, conversations, and organization tags.
Henry | PaiSmart Development | 14/04/2026 | Henry | 2:00 PM | 6:30 PM | 4:30 | Prepared application configuration profiles for local, Docker, and production environments, including database, Redis, Kafka, MinIO, Elasticsearch, JWT, and AI API settings.
Henry | PaiSmart Development | 15/04/2026 | Henry | 9:30 AM | 1:00 PM | 3:30 | Implemented the user domain model, user role handling, user repository, and password hashing utility for secure account storage.
Henry | PaiSmart Development | 15/04/2026 | Henry | 2:00 PM | 6:30 PM | 4:30 | Implemented JWT utilities for token generation, claim extraction, expiration checks, refresh checks, and invalid token handling.
Henry | PaiSmart Development | 16/04/2026 | Henry | 9:30 AM | 1:00 PM | 3:30 | Built the user registration API with validation for empty fields, duplicate usernames, password encryption, and basic response handling.
Henry | PaiSmart Development | 16/04/2026 | Henry | 2:00 PM | 6:30 PM | 4:30 | Built the login API, authenticated username and password, returned access token data, and prepared user information for the frontend auth store.
Henry | PaiSmart Development | 17/04/2026 | Henry | 9:30 AM | 1:00 PM | 3:30 | Implemented token cache support in Redis, including access token storage, refresh token storage, token blacklist checks, and active token tracking.
Henry | PaiSmart Development | 17/04/2026 | Henry | 2:00 PM | 6:30 PM | 4:30 | Implemented logout, logout-all, refresh-token, and current-user profile flows to complete the first version of account session management.
Henry | PaiSmart Development | 20/04/2026 | Henry | 9:30 AM | 1:00 PM | 3:30 | Configured Spring Security, CORS, stateless sessions, JWT authentication filtering, protected endpoints, and request attributes for user context.
Henry | PaiSmart Development | 20/04/2026 | Henry | 2:00 PM | 6:30 PM | 4:30 | Added default admin initialization and basic admin service logic so the project can be demonstrated and managed after startup.
Henry | PaiSmart Development | 21/04/2026 | Henry | 9:30 AM | 1:00 PM | 3:30 | Implemented file metadata persistence, including file MD5, original file name, total size, upload status, owner user ID, organization tag, and public/private flag.
Henry | PaiSmart Development | 21/04/2026 | Henry | 2:00 PM | 6:30 PM | 4:30 | Implemented file chunk metadata persistence to record chunk index, chunk MD5, storage path, and upload progress for resumable upload.
Henry | PaiSmart Development | 22/04/2026 | Henry | 9:30 AM | 1:00 PM | 3:30 | Implemented file type validation for supported document formats and clear rejection messages for unsupported or malformed file names.
Henry | PaiSmart Development | 22/04/2026 | Henry | 2:00 PM | 6:30 PM | 4:30 | Configured the MinIO client and upload bucket access so the backend can store chunks and final merged files.
Henry | PaiSmart Development | 23/04/2026 | Henry | 9:30 AM | 1:00 PM | 3:30 | Implemented the chunk upload endpoint, validated request parameters, accepted file parts, stored chunks, and recorded successful chunk state.
Henry | PaiSmart Development | 23/04/2026 | Henry | 2:00 PM | 6:30 PM | 4:30 | Implemented upload status query logic so the frontend can resume interrupted uploads from the last uploaded chunk.
Henry | PaiSmart Development | 24/04/2026 | Henry | 9:30 AM | 1:00 PM | 3:30 | Implemented the file merge endpoint, merged uploaded chunks, saved the final file, persisted file metadata, and cleaned temporary upload state.
Henry | PaiSmart Development | 24/04/2026 | Henry | 2:00 PM | 6:30 PM | 4:30 | Configured Kafka producers, consumers, topics, group IDs, JSON serialization, and the file-processing task message structure.
Henry | PaiSmart Development | 27/04/2026 | Henry | 9:30 AM | 1:00 PM | 3:30 | Implemented the Kafka file-processing consumer to trigger document parsing and vectorization after a file has been uploaded and merged.
Henry | PaiSmart Development | 27/04/2026 | Henry | 2:00 PM | 6:30 PM | 4:30 | Implemented Apache Tika parsing for uploaded documents, including file stream handling, text extraction, parsing errors, and empty-content handling.
Henry | PaiSmart Development | 28/04/2026 | Henry | 9:30 AM | 1:00 PM | 3:30 | Implemented text chunking logic for long documents, including Chinese text, mixed-language text, very small chunk size, empty text, and long paragraph cases.
Henry | PaiSmart Development | 28/04/2026 | Henry | 2:00 PM | 6:30 PM | 4:30 | Implemented embedding API integration and vectorization service logic to convert parsed document chunks into dense vector representations.
Henry | PaiSmart Development | 29/04/2026 | Henry | 9:30 AM | 1:00 PM | 3:30 | Configured Elasticsearch client access and implemented bulk indexing, index deletion by file MD5, and index-related service operations.
Henry | PaiSmart Development | 29/04/2026 | Henry | 2:00 PM | 6:30 PM | 4:30 | Created the knowledge-base Elasticsearch mapping with text fields, vector fields, file metadata, user ownership, organization tags, and public/private access fields.
Henry | PaiSmart Development | 30/04/2026 | Henry | 9:30 AM | 1:00 PM | 3:30 | Implemented index initialization on startup so the Elasticsearch knowledge-base index can be created automatically when missing.
Henry | PaiSmart Development | 30/04/2026 | Henry | 2:00 PM | 6:30 PM | 4:30 | Implemented hybrid search by combining keyword retrieval and vector retrieval, merging results, ranking them, and returning top knowledge chunks.
Henry | PaiSmart Development | 04/05/2026 | Henry | 9:30 AM | 1:00 PM | 3:30 | Implemented the hybrid search REST endpoint so frontend pages and agent tools can query the knowledge base with a natural-language question.
Henry | PaiSmart Development | 04/05/2026 | Henry | 2:00 PM | 6:30 PM | 4:30 | Implemented document management APIs for listing uploaded files, listing accessible files, generating download links, previewing files, and deleting documents.
Henry | PaiSmart Development | 05/05/2026 | Henry | 9:30 AM | 1:00 PM | 3:30 | Implemented the DeepSeek client and AI generation configuration for model URL, model name, API key, generation parameters, and prompt settings.
Henry | PaiSmart Development | 05/05/2026 | Henry | 2:00 PM | 6:30 PM | 4:30 | Implemented WebSocket configuration, chat WebSocket handler registration, WebSocket token access, and frontend connection routing.
Henry | PaiSmart Development | 06/05/2026 | Henry | 9:30 AM | 1:00 PM | 3:30 | Implemented the chat handler, connected user messages to the AI processing flow, and returned generated responses through the WebSocket session.
Henry | PaiSmart Development | 06/05/2026 | Henry | 2:00 PM | 6:30 PM | 4:30 | Implemented stop-response support so long AI responses can be interrupted and the WebSocket session can receive a stop confirmation.
Henry | PaiSmart Development | 07/05/2026 | Henry | 9:30 AM | 1:00 PM | 3:30 | Implemented conversation persistence for storing user questions, AI answers, usernames, and timestamps.
Henry | PaiSmart Development | 07/05/2026 | Henry | 2:00 PM | 6:30 PM | 4:30 | Implemented conversation history query APIs for users and administrators, including username and date-range filtering.
Henry | PaiSmart Development | 08/05/2026 | Henry | 9:30 AM | 1:00 PM | 3:30 | Built the Vue frontend layout, authenticated route structure, global menu, page container, auth store, route guards, and API request foundation.
Henry | PaiSmart Development | 08/05/2026 | Henry | 2:00 PM | 6:30 PM | 4:30 | Built frontend login, registration, current-user loading, logout handling, token storage, and basic authentication UI flow.
Henry | PaiSmart Development | 11/05/2026 | Henry | 9:30 AM | 1:00 PM | 3:30 | Built the knowledge-base frontend page with document table, upload dialog entry, delete action, preview/download actions, and search dialog entry.
Henry | PaiSmart Development | 11/05/2026 | Henry | 2:00 PM | 6:30 PM | 4:30 | Built the frontend upload queue with chunk upload, progress display, interruption state, resume upload, merge request, and upload task synchronization.
Henry | PaiSmart Development | 12/05/2026 | Henry | 9:30 AM | 1:00 PM | 3:30 | Built the chat frontend page with message list, input box, WebSocket store integration, response rendering, and basic interaction states.
Henry | PaiSmart Development | 12/05/2026 | Henry | 2:00 PM | 6:30 PM | 4:30 | Added Phase 1 regression tests for authentication, user management, upload, search, document management, chat, conversation, parsing, JWT, and utility services.
Henry | PaiSmart Development | 13/05/2026 | Henry | 9:30 AM | 1:00 PM | 3:30 | Started Phase 2 organization-scope work by implementing the organization tag entity, repository, database fields, and default organization initialization.
Henry | PaiSmart Development | 13/05/2026 | Henry | 2:00 PM | 6:30 PM | 4:30 | Implemented admin organization-tag APIs for creating tags, listing all tags, building the tree structure, editing tags, and deleting tags.
Henry | PaiSmart Development | 14/05/2026 | Henry | 9:30 AM | 1:00 PM | 3:30 | Implemented user organization assignment APIs so an administrator can assign one or more organization tags to a user.
Henry | PaiSmart Development | 14/05/2026 | Henry | 2:00 PM | 6:30 PM | 4:30 | Implemented user organization APIs for querying assigned tags, changing the primary organization, and loading allowed upload organizations.
Henry | PaiSmart Development | 15/05/2026 | Henry | 9:30 AM | 1:00 PM | 3:30 | Implemented organization-scope permission services, including effective tag lookup, admin checks, owner checks, public document checks, and organization membership checks.
Henry | PaiSmart Development | 15/05/2026 | Henry | 2:00 PM | 6:30 PM | 4:30 | Extended upload, document listing, and frontend organization pages for Phase 2 by adding organization tag selection, public/private metadata, user tag assignment UI, and organization-tag management UI.